## Living Document
School District of Milton
5- Year Capital Maintenance Plan
Edited 09/29/2014
|  |  | 2014-15 | 2015-16 | 2016-17 | 2018-19 | 2019-20 | No Time Frame | 5 year total
101 | East Elementary
1 | Paint East Hallway and main office - |  | 11640
Lockers, walls, and door casings
2 | Bathroom Renovations (eastside) |  |  | 125000
3 | Strip and Paint Gym Hallway |  |  | 14760
4 | Replace 4 folding classroom curtains |  |  |  | 21600
5 | Bathroom Renovations (westside) |  |  |  |  | 100000
6 | Replace Fire Alarm System |  |  |  |  | 32000
7 | Boiler Replacement | [5 empty] | 120000
8 | Replace gym floor - Terraflex | [5 empty] | 33347
| Yearly total: |  | 11640 | 139760 | 21600 | 132000 | 153347 |  | 458347
102 | West Elementary
1 | Abate Asbestos Tile - Cafeteria |  | 4389
2 | Project Design and final air clearance |  | 2800
3 | VCT Tile - cafeteria |  | 5062
4 | DDC Controls - Phase 1 |  |  | 57564
5 | Replace Univents- A/C units |  |  | 7000
in rooms 115, 117, 119
6 | DDC Controls - Phase 2 |  |  |  | 13340
7 | Remodel South Bathrooms |  |  |  | 100000
8 | Replace Exterior Windows |  |  |  |  | 150000
Single Pane vs. Double Pane
9 | Replace gym floor - Terraflex | [5 empty] | 33251
| Yearly Total: |  | 12251 | 64564 | 113340 | 150000 | 33251 |  | 373406
103 | Consolidated Elementary
1 | DDC Controls |  | 24500
2 | Replace Fire Alarm System |  |  | 25700
3 | Pavement Replacement |  |  |  | 49863
4 | Boiler Replacement | [5 empty] | 103000
| Yearly Total: |  | 24500 | 25700 | 49863 | 0 | 103000 |  | 203063
104 | Harmony Elementary
1 | Carpet Replacement - Front Office |  |  | 3200
| Yearly Total: |  | 0 | 3200 | 0 | 0 | 0 |  | 3200
150 | Northside Intermediate
1 | Carpet Replacement - by wing |  | 39977 | 39977 | 51790
2 | Replace front circle drive |  | 48761
3 | Roof Replacement IMC & 300 wing |  | 226293
4 | Roof Project Management |  | 13577 | 14041
5 | Roof Replacement 400 wing & gym |  |  | 234009
Modified-400 Ballasted EPDM- Gym
6 | Replace fire alarm system | [5 empty] | 65000
| Yearly Total: |  | 328608 | 288027 | 51790 | 0 | 65000 |  | 733425
200 | Middle School
1 | Walk off Mats at east entry & hallway |  | 10629
2 | DDC Controls - Phase 1 |  |  | 45000
3 | Replace clock - sound system |  |  | 22000
4 | Replace 4 science room sinks |  |  | 17500
5 | Air conditioning in band and lunch room |  |  | 30000
6 | DDC Controls - Phase 2 |  |  |  | 82455
7 | Replace pavement - east side |  |  |  | 20000
| Yearly Total: |  | 10629 | 114500 | 102455 | 0 | 0 |  | 227584
400 | High School
1 | Carpet replacement - 1994 Addition |  | 13641
118,119,120, & Corridor M & C
2 | Locker Painting (Phase 1) |  | 9880
3 | Univent Replacement Rooms 142-144 |  | 16858
4 | Controls for Rooms 142-144 |  | 3631
5 | Repair Blacktop by Tech Ed. |  | 12087
6 | Door Hardware Replacement |  |  | 74000
7 | Upgrade Security Cameras |  |  | 75000
8 | Replace Concrete at front entry |  |  | 27000
9 | Carpet replacement - 1999 Addition |  |  | 30000
10 | Locker Painting (Phase 2) |  |  | 8000
11 | Roof Replacement - |  |  |  | 237000
Sections 10, 12, 13, & 14
12 | Locker Painting (Phase 3) |  |  |  | 9500
13 | Resurface running track |  |  |  | 33200
14 | Roof Replacement- Section 11 |  |  |  |  | 260000
15 | Roof Replacement- Section 1 | [5 empty] | 248000
16 | Replace gym doors - Lower | [5 empty] | 24000
17 | Pool Modifications & Upgrades | [6 empty] | 1000000
(Construction Phase)
18 | Renovate office and provide | [6 empty] | 385000
secure entry sequence
19 | Replace Tennis Courts | [6 empty] | 250000
20 | Renovate front lobby area | [6 empty] | 112500
| Yearly Total: |  | 56097 | 214000 | 279700 | 260000 | 272000 |  | 1081797
811 | District Office/ Maintenance
1 | DDC Control - Web Supervisor |  | 6275
Install District Wide Security Cameras
| and Upgrade District Access Control |  | 415403
2 | Replace Shingle roof- section 1 |  |  | 40000
3 | Restore roof sections 2 & 3 | [5 empty] | 38000
| Yearly Total: |  | 421678 | 40000 | 0 | 0 | 38000 |  | 499678
980 | Schilberg Park
1 | Relamp Park & Stadium |  |  | 28000
2 | Add 100 stall blacktop parking lot |  |  |  | 112000
| Yearly Total: |  | 0 | 28000 | 112000 | 0 | 0 |  | 140000
|  | TOTALS: | 2014-15 | 2015-16 | 2016-17 | 2017-18 | 2018-19
|  |  | 865403 | 917751 | 730748 | 542000 | 664598
|  |  |  | 5 year total: |  | 3720500
Completed 2014 -15 Living Document Projects
Living Document Projects Schedule for Winter Break
Change Orders
[5 empty] | Orig. PO | New Amnt.
|  | Reduction in the amount of walk off tile at MMS |  |  | 10629 | 6687
|  | Additional undercut needed at NIS |  |  | 48761 | 49460.5
|  | Additional controls for MHS univents (3) |  |  | 3631 | 5894
|  | Fill Low Spot in cafeteria floor (WES) |  |  | 2162 | 2829